## Development_plan
Task# | Description | Tools | Comments | Date | Status | Resources
1 | Initialize the app |  |  | 2020-07-31 | Closed
2 | Define MVP |  |  | 2020-07-31 | Closed
3 | Create ER diagram |  |  | 2020-08-01 | Closed | ER_diagram.drawio
4 | Complete all attributes per entity |  |  | 2020-08-01 | Closed | ER_diagram.drawio
6 | Create Restful Routing Chart | Excel |  | 2020-08-01 | In progress
7 | Wireframing | https://app.diagrams.net/ | Define GUI based on Restful routs & ERD | 2020-08-02 | Closed | https://app.diagrams.net/
7 | Create application MVC framework | VS Code | Create folders | 2020-08-02 | Closed
8 | Configure config/config.json | VS Code | Set database | 2020-08-02 | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9 | Create models |  |  | 2020-08-02 | Closed
9.1 | Create Account model | npx sequelize model:generate --name ModelName --attributes: name1:dataType,… | models/account.js migrations/timestamp-create-account.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9.2 | Create Subaccount model |  | models/subaccount.js migrations/timestamp-create-subaccount.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9.3 | Create PaymentType model |  | models/paymenttype.js migrations/timestamp-create-payment-type.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9.4 | Create Status model |  | models/status.js migrations/timestamp-create-status.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9.5 | Create Expense model |  | models/expense.js migrations/timestamp-create-expense.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10 | Update models and create tables |  |  | 2020-08-02 | Open
10.1 | Update Account migration | VS Code | migrations/timestamp-create-account.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.11 | Update Account model | VS Code | models/account.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.12 | Create Accounts table | npx sequelize db:migrate | Check table with pgAdmin |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.2 | Update Subaccount model | VS Code | migrations/timestamp-create-subaccount.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.21 | Update Subaccount model | VS Code | models/Subaccount.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.22 | Create Subaccounts table | npx sequelize db:migrate | Check table with pgAdmin |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.3 | Update PaymentType migration | VS Code | migrations/timestamp-create-subaccount.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.31 | Update PaymentType model | VS Code | models/Subaccount.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.32 | Create PaymentTypes table | npx sequelize db:migrate | Check table with pgAdmin |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.4 | Update Status migration | VS Code | migrations/timestamp-create-status.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.41 | Update Status model | VS Code | models/Status.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.42 | Create Statuses table | npx sequelize db:migrate | Check table with pgAdmin |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.5 | Update Expense migration | VS Code | migrations/timestamp-create-expense.js |  | Closed | https://medium.com/@andrewoons/how-to-define-sequelize-associations-using-migrations-de4333bf75a7
10.51 | Update Expense model | VS Code | models/Expense.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10.52 | Create Expenses table | npx sequelize db:migrate | Check table with pgAdmin |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
11 | Create Seeders |  |  | 2020-08-02 | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
11.1 | Create seeder for Accounts table | npx sequelize seed:generate --name demo-accounts | seeders/timestamp-demo-accounts.js |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
11.11 | Import seeders into the table | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/timestamp-demo-accounts.js |  |  | Closed | https://git.generalassemb.ly/jdr-0622/sequelize-intro
11.2 | Create seeder for Subccounts table | npx sequelize seed:generate --name demo-subaccounts | seeders/timestamp-demo-subaccounts.js |  | Closed
11.21 | Import seeders into the table | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/timestamp-demo-subaccounts.js |  |  | Closed
11.3 | Create seeder for PaymentTypes table | npx sequelize seed:generate --name demo-paymentTypes | seeders/timestamp-demo-paymentTypes.js |  | Closed
11.31 | Import seeders into the table | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/timestamp-demo-paymentTypes.js |  |  | Closed
11.4 | Create seeder for Statuses table | npx sequelize seed:generate --name demo-statuses | seeders/timestamp-demo-statuses.js |  | Closed
11.41 | Import seeders into the table | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/timestamp-demo-statuses.js |  |  | Closed
11.5 | Create seeder for Expenses table | npx sequelize seed:generate --name demo-expenses | seeders/timestamp-demo-expenses.js |  | Closed
11.51 | Import seeders into the table | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/timestamp-demo-expenses.js |  |  | Closed
12 | Work on Expenses controller
12.01 | Create expensesController.js | Create file in controllers/expensesController.js | - Ini the file comparing with fruitsController.js - No routes still |  | Closed
12.02 | Update server.js | Update file /server.js | - Include app.use for cookieParser - Include app.use for expenses |  | Closed
12.03 | Create index.js for expenses | Create file /views/expenses/index.js | - Start with fruits.js code

## MVP features
Feature # | Feature | Priority | Status
1 | As a user I want to sign up on the application if I'm not registered | High
2 | As a user I want to log in the application if I'm already registered | High
3 | As a user I want to log out the application once I'm done with my expenses | High
4 | As a user I want to create an expense | High
7 | As a user I want to display my expenses | High
5 | As a user I want to update the expense | High
6 | As a user I want to delete the expense | High
8 | As a user I want to assign my expense to an account (created by me) | Low | Provide accounts by default
9 | As a user I want to assign my expense to a sub-account (created by me) | Low | Provide accounts by default
10 | As a user I want to assign my expense to a payment type (created by me) | Low | Provide accounts by default
11 | As a user I want to know the status of my expense | Low | Provide accounts by default
12 | As a user I want to analyze my application by period of dates | High
13 | As a user I want to analyze my application by account | Medium
14 | As a user I want to analyze my application by subaccount | Medium
15 | As a user I want to analyze my application by status | Medium
16 | As a user I want to analyze my application by payment type | Medium

## RESTFUL routing
User Resource
CRUD | HTTP Verb | REST-ful Route Name | File | Path localhost:3000/ | View/Template | Sequelize Method | Description
Read | GET | Homepage | server.js | / | res.render("users/index.ejs") | None | ExTracker app homepage with login/signup links
Read | GET | Sign Up | authController.js | /auth/signup | res.render("users/signup.ejs") | None | Render empty user sign up form
Create | POST | CREATE | authController.js | /auth | res.redirect(`/users/profile/${newUser.id}`) | User.create(req.body) | Create a new user
Read | GET | Log In | authController.js | /auth/login | res.render("users/login.ejs", { showMessage: false }); | None | Render empty user login form
Create | POST | CREATE | authController.js | /auth/login | res.redirect(`/users/profile/${foundUser.id}`); | User.findOne({ where: {username: req.body.username, password: req.body.password} }) | Create a new user session
Read | GET | Show/Profile | usersController.js | /users/profile/:id | res.render("users/profile.ejs", { user: userProfile, }) | User.findByPk(req.params.id) | Show User Detail/Profile
Update | PUT | UPDATE | usersController.js | /users/profile/:id | res.redirect(`/users/profile/${req.params.id}`) | User.update(req.body, {where: {id: req.params.id } } ) | Update an exisiting User
Delete | DELETE | DELETE | usersController.js | /users/:id | res.redirect("/") | User.destroy({where: {id: req.params.id } }) | Delete an existing User
Expense Resource
CRUD | HTTP Verb | REST-ful Route Name | File | Path localhost:3000/ | View/Template | Sequelize Method | Description
Read | GET | INDEX | expensesController.js | /expenses | res.render("index.ejs", { expenseIndex: expense, }); | Expense.findAll() | Render all expenses from DB
Read | GET | SHOW | expensesController.js | /expenses/:id | res.render("show.ejs", { fruit: fruit, }); | Expense.findByPk(req.params.id) | Render one expense from DB
Read | GET | NEW | expensesController.js | /expenses/new | new.ejs | none | Render empty expense form
Create | POST | CREATE | expensesController.js | /expenses | res.redirect("/expenses"); | Expense.create(req.body) | Create new instance of a expense and then redirect
Read | GET | EDIT | expensesController.js | /expenses/:id/edit | res.render("edit.ejs", { fruitEdit: foundFruit, seasons: allSeasons, }); | Expense.findByPk(req.params.id) | Render form with an expense
Update | PUT | UPDATE | expensesController.js | /expenses/:id | res.redirect("/expenses"); | Expense.update(req.body, {where: {id: req.params.id}}) | Updates an existing expense
Delete | DELETE | DELETE | expensesController.js | /expenses/:id | res.redirect("/expenses"); | Expense.destroy({ where: { id: req.params.id } }) | Deletes an expense

## Table definitions
Table | Expenses
Column | DataType | Length | Is Null? | Is PK? | Is FK? | Is Unique? | Default value?
id | Integer |  | No | Yes | No | Yes
date | Date |  | No | No | No | No | new Date()
description | Varchar | 255 | No | No | No | No | Pending expense description
amount | Money |  | No | No | No | No | 0
comment | Varchar | 255 | Yes | No | No | No
userId | Integer |  | No | No | Yes | No
accountId | Integer |  | No | No | Yes | No
subaccountId | Integer |  | No | No | Yes | No
paymentTypeId | Integer |  | No | No | Yes | No
statusId | Integer |  | No | No | Yes | No
Table | Accounts
Column | DataType | Length | Is Null? | Is PK? | Is FK? | Is Unique? | Default value?
id | Integer |  | No | Yes | No | Yes
description | Varchar | 255 | No | No | No | No | "Pending description"
createdAt | Date timestamp |  | No | No | No | No | new Date()
updatedAt | Date timestamp |  | No | No | No | No | new Date()
Table | Subaccounts
Column | DataType | Length | Is Null? | Is PK? | Is FK? | Is Unique? | Default value?
id | Integer |  | No | Yes | No | Yes
description | Varchar | 255 | No | No | No | No | "Pending description"
createdAt | Date timestamp |  | No | No | No | No | new Date()
updatedAt | Date timestamp |  | No | No | No | No | new Date()
Table | PaymentTypes
Column | DataType | Length | Is Null? | Is PK? | Is FK? | Is Unique? | Default value?
id | Integer |  | No | Yes | No | Yes
description | Varchar | 255 | No | No | No | No | "Pending description"
createdAt | Date timestamp |  | No | No | No | No | new Date()
updatedAt | Date timestamp |  | No | No | No | No | new Date()
Table | Status
Column | DataType | Length | Is Null? | Is PK? | Is FK? | Is Unique? | Default value?
id | Integer |  | No | Yes | No | Yes
description | Varchar | 255 | No | No | No | No | "Pending description"
fontColor | Varchar | 255 | Yes | No | No | No
backgroudColor | Varchar | 255 | Yes | No | No | No
createdAt | Date timestamp |  | No | No | No | No | new Date()
updatedAt | Date timestamp |  | No | No | No | No | new Date()

## Default Values
Table | Accounts
id | description
1 | Family
2 | Father
3 | Mother
4 | Son
5 | Daughter
Table | Subaccounts
id | description
1 | Education
2 | Enterteinment
3 | Food
4 | Vacations
5 | Clothing
6 | Health care
7 | Transportation
8 | Other necessities
Table | PaymentTypes
id | description
1 | Cash
2 | Credit card
3 | Bank transfer
4 | Prepaid card
5 | Other
Table | Status
id | description | fontColor | BackgroundColor
1 | Complete | #000000 | #F4F4F4
2 | Pending | #FFFFFF | #FF2600
Table | Expenses
id | date | description | amount | comment | userId | accountId | subaccountId | paymentTypeId | statusId
1 | "2020-07-15" | Restaurant Meal | 120 | Red Lobster | 1 | 1 | 2 | 2 | 1
2 | "2020-07-16" | Cinema | 20 |  | 1 | 3 | 2 | 1 | 1
3 | "2020-07-16" | Dentist | 40 |  | 1 | 2 | 6 | 2 | 1
4 | "2020-07-20" | Taxes | 150 |  | 1 | 1 | 8 | 3 | 2
5 | "2020-07-20" | Car Wash | 20 |  | 1 | 3 | 8 | 1 | 1
6 | "2020-07-20" | Tennis shoes | 80.5 | Amazon | 1 | 2 | 5 | 4 | 1
7 | "2020-07-31" | New laptop | 500 | Best Buy | 1 | 4 | 1 | 2 | 1
8 | "2020-08-01" | New smartphone | 300 | Best Buy | 1 | 3 | 8 | 2 | 1
9 | "2020-08-01" | Flight tickets | 800 | American Airlines | 1 | 1 | 4 | 2 | 1
10 | "2020-08-02" | Suitcases | 120 |  | 1 | 1 | 4 | 2 | 2

## Resources
Express documentation | https://git.generalassemb.ly/jdr-0622/express-intro
Express documentation | https://git.generalassemb.ly/jdr-0622/url_and_query_params
Express documentation | https://git.generalassemb.ly/jdr-0622/intro_to_Rest
Express documentation (Pokemon) | https://git.generalassemb.ly/jdr-0622/Pokemon-Express
Express documentation | https://git.generalassemb.ly/jdr-0622/hw-express-params
Express documentation | https://git.generalassemb.ly/jdr-0622/MVC
Express documentation | https://git.generalassemb.ly/jdr-0622/express-controllers
Express documentation | https://git.generalassemb.ly/jdr-0622/express-user-model
Sequalize documentation | https://git.generalassemb.ly/jdr-0622/sequelize-intro
Sequelize fruit-app | https://git.generalassemb.ly/jdr-0622/sequelize-intro#create-a-fruit---post-route
Routing chart | https://docs.google.com/spreadsheets/d/14-LHKXLtEkp_vKEz3qSKjREnrmSyzQ9fimTlmrPsZsQ/edit#gid=0
Sequelize documentation | https://git.generalassemb.ly/jdr-0622/sequelize-associations
Sequelize pokemon-app | https://git.generalassemb.ly/jdr-0622/Pokemon-Express#day-5
Sequelize pokemon-app | https://git.generalassemb.ly/marcwright-rem/pokemon-express-sequelize6
Async functions | https://git.generalassemb.ly/jdr-0622/Review-JD-0622
JWT-authorizations | https://git.generalassemb.ly/jdr-0622/jwt-auth
JWT website | https://jwt.io/
User authentication | https://git.generalassemb.ly/jdr-0622/jwt-auth#user-authentication
Sequelize pokemon-app | https://git.generalassemb.ly/jdr-0622/Pokemon-Express/blob/master/README.md#day-6
Project 2 documentation | https://git.generalassemb.ly/jdr-0622/project-2
Project 2 starter - Marc | https://github.com/marcwright/deere-project2-starter
Markdown documentation | https://guides.github.com/pdfs/markdown-cheatsheet-online.pdf
User stories & Wireframe | https://git.generalassemb.ly/jdr-0622/wireframes-and-user-stories