## Development_plan
Task# | Description | Tools | Comments | Date | Status | Resources
1 | Initialize the app |  |  | 2020-07-31 | Closed
2 | Define MVP |  |  | 2020-07-31 | Closed
3 | Create ER diagram |  |  | 2020-08-01 | Closed | ER_diagram.drawio
4 | Complete all attributes per entity |  |  | 2020-08-01 | Closed | ER_diagram.drawio
6 | Create Restful Routing Chart | Excel |  | 2020-08-01 | In progress
7 | Wireframing | https://app.diagrams.net/ | Define GUI based on Restful routs & ERD | 2020-08-02 | In progress | https://app.diagrams.net/
7 | Create application MVC framework | VS Code | Create folders | 2020-08-02 | Open
8 | Configure config/config.json | VS Code | Set database | 2020-08-02 | Open | https://git.generalassemb.ly/jdr-0622/sequelize-intro
9 | Create models | npx sequelize model:generate --name ModelName --attributes: name1:dataType,name2:dataType,name3:dataType | models/ModelName.js migrations/timestamp-create-ModelName.js | 2020-08-02 | Open | https://git.generalassemb.ly/jdr-0622/sequelize-intro
10 | Crete seeders | npx sequelize seed:generate --name demo-fruits | seeders/timestamp-demo-fruits | 2020-08-02 | Open | https://git.generalassemb.ly/jdr-0622/sequelize-intro
11 | Create tables | npx sequelize db:migrate | Create tables (Uppercase and plural) | 2020-08-02 | Open | https://git.generalassemb.ly/jdr-0622/sequelize-intro
12 | Import seeders' data | (1) sequelize db:seed:all OR (2) sequelize db:seed --seed seeders/20200726194746-demo-users.js | 1 - Will import ALL seeders 2 - Will import only the specified file | 2020-08-02 | Open | https://git.generalassemb.ly/jdr-0622/sequelize-intro
13 | DEFINE REST OF THE PLAN |  |  | 2020-08-02

## MVP features
Feature # | Feature | Priority | Status
1 | As a user I want to sign up on the application if I'm not registered | High
2 | As a user I want to log in the application if I'm already registered | High
3 | As a user I want to log out the application once I'm done with my expenses | High
4 | As a user I want to create an expense | High
7 | As a user I want to display my expenses | High
5 | As a user I want to update the expense | High
6 | As a user I want to delete the expense | High
8 | As a user I want to assign my expense to an account (created by me) | Low | Provide accounts by default
9 | As a user I want to assign my expense to a sub-account (created by me) | Low | Provide accounts by default
10 | As a user I want to assign my expense to a payment type (created by me) | Low | Provide accounts by default
11 | As a user I want to know the status of my expense | Low | Provide accounts by default
12 | As a user I want to analyze my application by period of dates | High
13 | As a user I want to analyze my application by account | Medium
14 | As a user I want to analyze my application by subaccount | Medium
15 | As a user I want to analyze my application by status | Medium
16 | As a user I want to analyze my application by payment type | Medium

## RESTFUL routing
User Resource
CRUD | HTTP Verb | REST-ful Route Name | File | Path localhost:3000/ | View/Template | Sequelize Method | Description
Read | GET | Homepage | server.js | / | res.render("users/index.ejs") | None | ExTracker app homepage with login/signup links
Read | GET | Sign Up | authController.js | /auth/signup | res.render("users/signup.ejs") | None | Render empty user sign up form
Create | POST | CREATE | authController.js | /auth | res.redirect(`/users/profile/${newUser.id}`) | User.create(req.body) | Create a new user
Read | GET | Log In | authController.js | /auth/login | res.render("users/login.ejs", { showMessage: false }); | None | Render empty user login form
Create | POST | CREATE | authController.js | /auth/login | res.redirect(`/users/profile/${foundUser.id}`); | User.findOne({ where: {username: req.body.username, password: req.body.password} }) | Create a new user session
Read | GET | Show/Profile | usersController.js | /users/profile/:id | res.render("users/profile.ejs", { user: userProfile, }) | User.findByPk(req.params.id) | Show User Detail/Profile
Update | PUT | UPDATE | usersController.js | /users/profile/:id | res.redirect(`/users/profile/${req.params.id}`) | User.update(req.body, {where: {id: req.params.id } } ) | Update an exisiting User
Delete | DELETE | DELETE | usersController.js | /users/:id | res.redirect("/") | User.destroy({where: {id: req.params.id } }) | Delete an existing User
Expense Resource
CRUD | HTTP Verb | REST-ful Route Name | File | Path localhost:3000/ | View/Template | Sequelize Method | Description
Read | GET | INDEX | expensesController.js | /expenses | res.render("index.ejs", { expenseIndex: expense, }); | Expense.findAll() | Render all expenses from DB
Read | GET | SHOW | expensesController.js | /expenses/:id | res.render("show.ejs", { fruit: fruit, }); | Expense.findByPk(req.params.id) | Render one expense from DB
Read | GET | NEW | expensesController.js | /expenses/new | new.ejs | none | Render empty expense form
Create | POST | CREATE | expensesController.js | /expenses | res.redirect("/expenses"); | Expense.create(req.body) | Create new instance of a expense and then redirect
Read | GET | EDIT | expensesController.js | /expenses/:id/edit | res.render("edit.ejs", { fruitEdit: foundFruit, seasons: allSeasons, }); | Expense.findByPk(req.params.id) | Render form with an expense
Update | PUT | UPDATE | expensesController.js | /expenses/:id | res.redirect("/expenses"); | Expense.update(req.body, {where: {id: req.params.id}}) | Updates an existing expense
Delete | DELETE | DELETE | expensesController.js | /expenses/:id | res.redirect("/expenses"); | Expense.destroy({ where: { id: req.params.id } }) | Deletes an expense

## Resources
Express documentation | https://git.generalassemb.ly/jdr-0622/express-intro
Express documentation | https://git.generalassemb.ly/jdr-0622/url_and_query_params
Express documentation | https://git.generalassemb.ly/jdr-0622/intro_to_Rest
Express documentation (Pokemon) | https://git.generalassemb.ly/jdr-0622/Pokemon-Express
Express documentation | https://git.generalassemb.ly/jdr-0622/hw-express-params
Express documentation | https://git.generalassemb.ly/jdr-0622/MVC
Express documentation | https://git.generalassemb.ly/jdr-0622/express-controllers
Express documentation | https://git.generalassemb.ly/jdr-0622/express-user-model
Sequalize documentation | https://git.generalassemb.ly/jdr-0622/sequelize-intro
Sequelize fruit-app | https://git.generalassemb.ly/jdr-0622/sequelize-intro#create-a-fruit---post-route
Routing chart | https://docs.google.com/spreadsheets/d/14-LHKXLtEkp_vKEz3qSKjREnrmSyzQ9fimTlmrPsZsQ/edit#gid=0
Sequelize documentation | https://git.generalassemb.ly/jdr-0622/sequelize-associations
Sequelize pokemon-app | https://git.generalassemb.ly/jdr-0622/Pokemon-Express#day-5
Sequelize pokemon-app | https://git.generalassemb.ly/marcwright-rem/pokemon-express-sequelize6
Async functions | https://git.generalassemb.ly/jdr-0622/Review-JD-0622
JWT-authorizations | https://git.generalassemb.ly/jdr-0622/jwt-auth
JWT website | https://jwt.io/
User authentication | https://git.generalassemb.ly/jdr-0622/jwt-auth#user-authentication
Sequelize pokemon-app | https://git.generalassemb.ly/jdr-0622/Pokemon-Express/blob/master/README.md#day-6
Project 2 documentation | https://git.generalassemb.ly/jdr-0622/project-2
Project 2 starter - Marc | https://github.com/marcwright/deere-project2-starter
Markdown documentation | https://guides.github.com/pdfs/markdown-cheatsheet-online.pdf
User stories & Wireframe | https://git.generalassemb.ly/jdr-0622/wireframes-and-user-stories